SYNTHETIC DATA  ·  ILLUSTRATIVE EXAMPLE  ·  NOT AN APPROVAL RECORD

# Project Cost and Revenue Approval Report — Example

Fictional T&M scenario · Northstar Retail commerce platform · September 2026 to February 2027

Purpose. This fully populated example demonstrates how to present staffing, project economics and approval checks. All names, rates, volumes and amounts are synthetic; the document is not an approval record and must not be used as a customer commitment.

# Report identification

| Field | Project details | Field | Project details |
| --- | --- | --- | --- |
| Project / client | Commerce platform modernization / Northstar Retail (fictional) | Report ID / version | EX-2026-09 / 1.0 |
| Scenario / model | Base case / Time & Material | Prepared by / date | Sample PM / 23 Sep 2026 |
| Estimate period | 01 Sep 2026 – 28 Feb 2027 | Currency / price basis | PLN / net of VAT |

## Decision requested

Select one outcome after reviewing the inputs, exclusions and reconciliations in this report.

☐ Approve   ☐ Approve with conditions   ☐ Return for revision   ☐ Reject     No decision recorded — illustrative data only

| Approver | Name | Decision / conditions | Date / signature |
| --- | --- | --- | --- |
| Delivery / Project Manager | Pending assignment | Pending — example only | Not signed |
| Finance | Pending assignment | Pending — definitions to confirm | Not signed |
| Commercial / Account owner | Pending assignment | Pending — example only | Not signed |

# 1. Commercial and delivery assumptions  ·  SYNTHETIC EXAMPLE

Record the approved baseline and point each input to an estimate, contract clause or source record.

| Assumption | Approved value / scope | Evidence or owner |
| --- | --- | --- |
| Commercial model and revenue trigger | T&M; revenue = planned hours × sell rate × modeled billable share; no milestone or outcome revenue | Synthetic model; contract clause not supplied |
| Staffing, seniority and locations | 12 role profiles across Poland, Portugal and Romania; Principal, Lead, Senior, Mid and Junior | Illustrative profile in this report |
| Work calendar and capacity | Monthly hours per FTE: 176, 176, 160, 168, 152, 160; FTE multiplied by monthly hours | Synthetic calendar assumption |
| Rate card and billability | Synthetic PLN/hour cost and sell rates by role; billable share ranges from 50% to 100% | No approved rate card attached |
| Other project costs | Cloud, software and travel: Poland PLN 31,000; Portugal PLN 11,000; Romania PLN 9,000 | Synthetic cash operating costs |
| Overhead and D&A | Support overhead = 4% of direct labor; D&A = Poland PLN 10,800, Portugal PLN 6,000, Romania PLN 5,400 | Illustrative allocation; Finance to confirm |
| Exclusions | VAT, taxes, financing, currency FX, contingency and unmodeled costs excluded; no price escalation modeled | Illustrative scope only |
| Scenario treatment | Single base case; no probability weighting or contingency scenario included | Scenario owner: sample PM |

## Financial measure definitions

Use one approved definition throughout the total, location and seniority views.

| Measure | Finance-approved formula and scope | Allocation or source basis |
| --- | --- | --- |
| Total cost | Direct labor + cash operating costs + 4% support overhead + D&A | Planned amount; synthetic allocation |
| Project profit | Revenue less total project cost above | Net revenue; estimate period |
| LM | Illustrative: labor-attributed revenue less direct labor cost; percentage = LM / labor-attributed revenue | Role-level labor and T&M revenue |
| PM | Illustrative: project profit after all modeled costs; percentage = profit / revenue | Fully loaded project cost |
| EBIDA / EBITDA | Illustrative EBITDA-style proxy: revenue less labor, cash operating costs and support overhead; before D&A | EBIDA terminology/formula requires Finance confirmation |

Illustrative definitions only. LM is shown as labor-attributed revenue less direct labor cost; LM% is LM divided by labor-attributed revenue. PM is shown as project profit after the fully loaded cost below; PM% is project profit divided by revenue. The requested EBIDA line is presented as an EBITDA-style proxy: revenue less labor, allocated cash operating expenses and allocated support overhead, before depreciation and amortization. These are demonstration formulas only; Finance must confirm the organization’s official definitions and allocation policy before real approval.

# 2. Staffing ramp up  ·  SYNTHETIC EXAMPLE

Show when each group starts and how planned active capacity accumulates over the estimate period.

Figure 1. Synthetic monthly active FTE by delivery location. The profile is illustrative and uses the staffing start plan shown below.

| Period / start | Location | Role / seniority | New joiners | Active FTE | First billable date |
| --- | --- | --- | --- | --- | --- |
| Sep 2026 | Poland | Technical lead / Lead | 1 | 1 | Sep 2026 |
| Sep 2026 | Poland | Backend engineer / Senior | 1 | 1 | Sep 2026 |
| Sep 2026 | Poland | Project manager / Senior | 1 | 0.5 | Sep 2026 |
| Sep 2026 | Poland | Product designer / Senior | 1 | 0.5 | Sep 2026 |
| Sep 2026 | Romania | DevOps engineer / Senior | 1 | 1 | Sep 2026 |
| Oct 2026 | Poland | Backend engineer / Senior | 1 | 1 | Oct 2026 |
| Oct 2026 | Poland | QA engineer / Mid | 1 | 0.5 | Oct 2026 |
| Oct 2026 | Portugal | Principal architect / Principal | 1 | 0.25 | Oct 2026 |
| Oct 2026 | Portugal | Backend engineer / Senior | 1 | 0.5 | Oct 2026 |
| Oct 2026 | Portugal | Business analyst / Mid | 1 | 0.5 | Oct 2026 |
| Nov 2026 | Portugal | QA engineer / Mid | 1 | 0.5 | Nov 2026 |
| Nov 2026 | Romania | Backend engineer / Mid | 1 | 1 | Nov 2026 |
| Dec 2026 | Portugal | Backend engineer / Senior | 1 | 1 | Dec 2026 |
| Dec 2026 | Romania | Backend engineer / Mid | 1 | 1 | Dec 2026 |
| Jan 2027 | Romania | Frontend developer / Junior | 1 | 1 | Jan 2027 |

Illustrative reconciliation. Active capacity is derived from the role-level monthly FTE profiles; revenue uses planned hours and the modeled billable share. Rates, hours, start dates and billable dates are fictional assumptions pending source evidence.

# 3. Executive economics and team pyramid  ·  SYNTHETIC EXAMPLE

Present approved totals first, then show how the same economics distribute across delivery locations.

## Whole-project summary

| Measure | Amount | Rate / percentage | Definition / note |
| --- | --- | --- | --- |
| Total project revenue | PLN 2,032,564 | — | T&M planned hours × sell rate × billable share |
| Total project cost | PLN 1,414,467 | — | Labor + cash ops + 4% overhead + D&A |
| Project profit | PLN 618,097 | 30.4% | Revenue less total project cost |
| EBIDA / EBITDA proxy | PLN 640,297 | 31.5% | Illustrative EBITDA-style; before D&A |
| LM (illustrative) | PLN 742,884 | 36.5% | Revenue less direct labor cost |
| PM (illustrative) | PLN 618,097 | 30.4% | Illustrative fully loaded project profit |

## Team pyramid by seniority

Concurrent staffing snapshot at February 2027 (the peak month). Lead is shown separately from Senior. Total: 12.75 FTE. Headcount is not inferred from fractional FTE assignments.

|  |  |  | Principal · 0.25 FTE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Lead · 1 FTE |  |  |  |  |  |  |
|  | Senior · 5.5 FTE |  |  |  |  |  |  |  |
| Mid · 5 FTE |  |  |  |  |  |  |  |  |
| Junior · 1 FTE |  |  |  |  |  |  |  |  |

## Economics by location

Repeat a row for each location. LM and PM must use the Finance-approved definitions recorded on page 2.

| Location | Total cost | Revenue | Profit | EBIDA / EBITDA | LM amount / % | PM amount / % |
| --- | --- | --- | --- | --- | --- | --- |
| Poland | PLN 766,389 | PLN 1,039,376 | PLN 272,987 | PLN 283,787 | PLN 342,656 / 33.0% | PLN 272,987 / 26.3% |
| Portugal | PLN 354,126 | PLN 540,436 | PLN 186,310 | PLN 192,310 | PLN 216,276 / 40.0% | PLN 186,310 / 34.5% |
| Romania | PLN 293,952 | PLN 452,752 | PLN 158,800 | PLN 164,200 | PLN 183,952 / 40.6% | PLN 158,800 / 35.1% |
| TOTAL | PLN 1,414,467 | PLN 2,032,564 | PLN 618,097 | PLN 640,297 | PLN 742,884 / 36.5% | PLN 618,097 / 30.4% |

Allocation rule (illustrative). Direct labor and revenue remain tied to role-level profiles. Each location’s cloud, software and travel costs, support overhead (4% of labor cost), and depreciation/amortization are allocated to its location/seniority rows in proportion to that segment’s direct labor cost. This allocation is for demonstration only.

Pyramid basis. Specify whether the pyramid shows people or FTE. Reconcile both headcount and FTE to the ramp-up schedule; do not infer a hierarchy for a role family with a different seniority scale.

# 4. Cost and revenue by location and seniority  ·  SYNTHETIC EXAMPLE

Every row represents the intersection of one delivery location and one seniority. Planned FTE is the February 2027 period-end snapshot; cost and revenue cover all six months. Add rows as needed and reconcile totals to page 3.

## Cost breakdown  ·  SYNTHETIC EXAMPLE

| Location | Seniority | Planned FTE | Labor / vendor cost | Other allocated cost | Total cost |
| --- | --- | --- | --- | --- | --- |
| Poland | Lead | 1 | PLN 198,400 | PLN 19,839 | PLN 218,239 |
| Poland | Senior | 2.5 | PLN 410,960 | PLN 41,094 | PLN 452,054 |
| Poland | Mid | 1 | PLN 87,360 | PLN 8,736 | PLN 96,096 |
| Portugal | Principal | 0.25 | PLN 34,680 | PLN 3,206 | PLN 37,886 |
| Portugal | Senior | 2 | PLN 157,040 | PLN 14,517 | PLN 171,557 |
| Portugal | Mid | 2 | PLN 132,440 | PLN 12,243 | PLN 144,683 |
| Romania | Senior | 1 | PLN 124,000 | PLN 11,603 | PLN 135,603 |
| Romania | Mid | 2 | PLN 106,400 | PLN 9,956 | PLN 116,356 |
| Romania | Junior | 1 | PLN 38,400 | PLN 3,593 | PLN 41,993 |
| TOTAL |  | 12.75 | PLN 1,289,680 | PLN 124,787 | PLN 1,414,467 |

## Revenue breakdown  ·  SYNTHETIC EXAMPLE

| Location | Seniority | Revenue basis / unit | Revenue | Share of total | Source / trigger |
| --- | --- | --- | --- | --- | --- |
| Poland | Lead | 992 planned hours | PLN 285,696 | 14.1% | Synthetic rate card; T&M |
| Poland | Senior | 2,520 planned hours | PLN 593,520 | 29.2% | Synthetic rate card; T&M |
| Poland | Mid | 728 planned hours | PLN 160,160 | 7.9% | Synthetic rate card; T&M |
| Portugal | Principal | 204 planned hours | PLN 44,370 | 2.2% | Synthetic rate card; T&M |
| Portugal | Senior | 1,208 planned hours | PLN 271,800 | 13.4% | Synthetic rate card; T&M |
| Portugal | Mid | 1,288 planned hours | PLN 224,266 | 11.0% | Synthetic rate card; T&M |
| Romania | Senior | 992 planned hours | PLN 191,952 | 9.4% | Synthetic rate card; T&M |
| Romania | Mid | 1,120 planned hours | PLN 196,000 | 9.6% | Synthetic rate card; T&M |
| Romania | Junior | 480 planned hours | PLN 64,800 | 3.2% | Synthetic rate card; T&M |
| TOTAL |  | 9,532 planned hours | PLN 2,032,564 | 100.0% | Illustrative only |

Allocation rule. Show how shared costs and revenue are allocated across seniority and location. Any unallocated amount must be listed separately and must reconcile to the project total.

# 5. EBIDA / EBITDA by location and seniority  ·  SYNTHETIC EXAMPLE

Use the exact measure approved by Finance. Show its components, allocation basis and reconciliation to the whole-project figure.

| Location | Seniority | Allocated revenue | Allocated operating cost | EBIDA / EBITDA | Margin % |
| --- | --- | --- | --- | --- | --- |
| Poland | Lead | PLN 285,696 | PLN 215,164 | PLN 70,532 | 24.7% |
| Poland | Senior | PLN 593,520 | PLN 445,684 | PLN 147,836 | 24.9% |
| Poland | Mid | PLN 160,160 | PLN 94,741 | PLN 65,419 | 40.8% |
| Portugal | Principal | PLN 44,370 | PLN 37,244 | PLN 7,126 | 16.1% |
| Portugal | Senior | PLN 271,800 | PLN 168,651 | PLN 103,149 | 38.0% |
| Portugal | Mid | PLN 224,266 | PLN 142,232 | PLN 82,034 | 36.6% |
| Romania | Senior | PLN 191,952 | PLN 133,112 | PLN 58,840 | 30.7% |
| Romania | Mid | PLN 196,000 | PLN 114,218 | PLN 81,782 | 41.7% |
| Romania | Junior | PLN 64,800 | PLN 41,222 | PLN 23,578 | 36.4% |
| TOTAL |  | PLN 2,032,564 | PLN 1,392,267 | PLN 640,297 | 31.5% |

## Reconciliation and approval checks  ·  SYNTHETIC EXAMPLE

| Control | Evidence / result |
| --- | --- |
| Location totals equal whole-project totals | PASS — all amount variances PLN 0; synthetic figures |
| Location/seniority rows cover the modeled staffing plan | PASS — all 12 role profiles mapped; peak capacity 12.75 FTE |
| Revenue trigger and units match commercial model | ILLUSTRATIVE — T&M planned hours; contract evidence not supplied |
| Rates and costs have an approved source | PENDING — all rates and expenses are synthetic |
| LM, PM and EBIDA definitions approved by Finance | PENDING — sample definitions only; approval required |

## Open conditions and decision record  ·  SYNTHETIC EXAMPLE

| Condition / unresolved assumption | Owner | Due date | Resolution / approver |
| --- | --- | --- | --- |
| Replace synthetic cost/sell rates and expense inputs with approved source data | Commercial / PM | Before real approval | Open — example only |
| Approve LM, PM, EBIDA naming, formulas and allocation policy | Finance | Before real approval | Open — no sign-off recorded |

Release gate. This sample intentionally remains unsigned. Replace synthetic inputs, attach approved source files, confirm Finance definitions and record approver decisions before using a real estimate.